## Slide 1: GPRO DELIVERY PARTNER Onboarding

## Slide 2: EDUCATION AT URBAN GREEN
Education Team roles/responsibilities
GPRO news and expected education updates
Partner expectations and training projections

## Slide 3: INSTRUCTOR AGREEMENTS
Debrief Instructor Training Session (if applicable)
Instructor Training Follow-Up
  Urban Green will reach out to instructors directly to obtain signed copies of the GPRO Certified Instructor Agreement
  Instructors must sign this Agreement to gain access to their teaching materials
  Teaching materials are on the GPRO Website’s Instructor Portal

## Slide 4: PUBLIC VS. PRIVATE CLASSES
Private Course Series: Partner plans a class with a private company or organization
Public Course Series: Partner hosts a class open to the community and advertises it to fill seats

## Slide 5: PROGRAM LAUNCH EXAMPLE TIMELINE
Date | Owner | Action Item
12 Weeks | UGC | Urban Green and Partner check in about drafting a press release using the Press Release Template, social media posts, email blasts, and registration page language.
10 Weeks-ongoing | Partner | Field clients, instructors, members, and partners for willing participants. Some of the best connections in the industry are directly from instructors and clients. They can help branch out and connect to even more people if they like what they see.
8 Weeks | Partner | Schedule first course with Urban Green Council at least two months in advance, which includes: Scheduling an instructor Confirming a venue This advanced notice is required for the first class since there are unique steps to course launch.
8 Weeks | Partner | Using the templates provided and approved language from Urban Green, start drafting public outreach campaign.
8 Weeks | Partner | Send first e-blast to public listservs, members, clients, partners, etc.
6 Weeks | Partner | Request that members and clients assist with outreach in their own newsletters, e-blasts, and social media communities using pre-drafted language.
4 Weeks | Partner | Continue to execute personal outreach to the public and through instructors, members, clients, and anyone relevant in your professional network; this includes phone calls and emails from you directly
4 Weeks | Partner | Send second e-blast, newsletter or press blast
2 Weeks | Partner | Send third e-blast
1 Week | Partner | Check in with Urban Green about course registration
1 week | Partner | Send fourth and final public outreach blast
Class! | Partner | FIRST COURSE TAKES PLACE!

## Slide 6: YOUR FIRST CLASS
Access the Partner Portal on the GPRO Website
Partner Portal (demo):
‘Schedule a Class’ Form
Materials Order Form
Roster Template
Resources

## Slide 7: CAPTURING ATTENDANCE
GPRO is a Certificate Course; attendees are eligible for the exam and certificate only if they were present for all instructional hours
It is REQUIRED to submit sign-in sheets, which indicate that students were present for all instructional hours
A sign in sheet template is located on the Partner Portal

## Slide 8: PROCTORS
Proctors administer the GPRO exam
Since Urban Green Council will be in direct contact with proctors for exam duties, please connect us with your proctors for exam administration
GPRO Certified Instructors and Certificate Holders are NOT permitted to proctor

## Slide 9: STUDENT EXAM RESULTS
Partners are expected to submit rosters with student names and email addresses.
Students will receive their scores directly via email about two weeks after they take their exams.
The designated partner contact will receive an exam report containing all student scores after they are released to students

## Slide 10: STUDENT CERTIFICATES
If a student passes an exam, the same email that contains their exam results will also come with a PDF attachment of their GPRO Certificate.
If a student is interested in a hard copy of their certificate on cardstock paper or other GPRO swag, direct them to the GPRO Store (gpro.org/store).

## Slide 11: INVOICING
Review invoicing procedure

## Slide 12
FAQs
How do you display your GPRO credential on your email signature or resume?
Johnny Appleseed, RA, LEED AP O+M, GPRO: O&M
Title
Company

## Slide 13
FAQs
Are there any prerequisites?
There are no prerequisites to take GPRO; however, all courses assume prior knowledge in the respective trade, except GPRO Fundamentals of Building Green, which is appropriate for a range of audiences.

## Slide 14
FAQs
Are continuing education units (CEUs) available for GPRO courses?
Fundamentals of Building Green | 4 CEUs
Construction Management | 10 CEUs
Electrical Systems | 10 CEUs
Plumbing | 10 CEUs
Mechanical | 12 CEUs
Operations & Maintenance Essentials | 12 CEUs
Yes, GBCI, AIA, and PDH credits are available for all GPRO courses, based on the number of curriculum hours.